## Sheet1
TASK LIST FOR PR1
SN | TASK | FUNCTION | Assinged to | Deadline_Time | Priority
1 | USB PROTOCOL DEFINITION | define the usb protocol definition | Balaji | 2013-12-05
2 | BLE Pairing Procedure | write the code for ble pairing procedure. And test the demo | Balaji | 2013-12-02 | High | closed without considering the bond info store funtion (need to be considered before system enter into off mode)
3 | Power consumption of all interfaces | Test power consumed by all pheripherals by enabling and disabling | Punith | 2013-12-02 | High
4 | Configuration stored in NVMC | Store all default configuration including current time and alaram time and nor pointers in non voltaile memory | Sudhir | 2013-12-02 | Low
5 | Daily activity | Need to confirmed by TBD | Punith/Sudhir
6 | Alarm | Need to confirmed by TBD | Sudhir
7 | Fuel guage | Need to write code once hardware comes | Sudhir/Punith
8 | Proximty Sensor | Need to write code once hardware comes | Punith/Sudhir
9 | Bootloader integration BLE | Need to do UART (& SPI) bootloader integration with BLE. Led should blink untill device enters from dfu mode to device mode . This is new requirement | Balaji | 2013-12-04 | Low
10 | Nor erase Procedure | Erase is need to be taken care by device side for every read operation from application. | Sudhir | 2013-12-05 | Low
11 | Nor mem full | Need to overwrite the old data. SO no need to take of old data is transmitter or not. | Sudhir | 2013-12-04 | Low
12 | LED indication when memory full | LED will indicate contineously red and orange contineously untill synchroniztion with appliction happen.But it will take more power if user don’t synchronized with application for long time.So need to clarify by TBD.Right now it is contineous blinking . | Punith. |  | Low
13 | Temperature measurement from Nordic and BOSCH | Right now we are using timeout for temperature measurement from Nordic and BOSCH. Test wheteher we are getting room temperature or not. | Punith | 2013-12-03 | Low
14 | Size of single charecteristic size | what will be size of single charecteristic in code | Balaji | 2013-12-03 | High | approximately 148 bytes (tested with a characteristic which has write and notify property)
15 | Current consumption from charecteristic and services | Find is there any difference in current consumption when we have more services and charecteristic | Balaji | 2013-12-03 | High
16 | Data transmission from ble to appliction ( BLE data download ) | Get ack from application for every 1000 bytes send from NOR to BLE.if data in NOR is less than 1000 bytes indicate that nor don’t has enough data. | Punith | 2013-12-03 | Low
17 | FTDI to SPI development Kit | with sample code work with development kit | Balaji/Punith/Sudhir |  | High
18 | Local buffer in main. | Allocate local buffer in main ,to reduce NOR utilizaton frequently. If it don’t work go for NVM | Sudhir | 2013-12-04 | High
19 | Accelerometer | access acceleromter wth spi in PR1 | Punith |  | Low
20 | Factory reset | Upon factory reset ,need to erase all data in NOR | Sudhir | 2013-12-05 | Low